## Read Me
Highway Project Risk Register — Standard Categories and Risks
Purpose
A standardized list of risk categories and default risk events for highway Major Projects, suitable for use across non-complex, moderately complex, and most complex highway projects. The list is synthesized from FHWA Major Projects guidance, Caltrans PRMHB, WSDOT CEVP/CRA, FDOT PMG 405 (CSRA for Major Projects), GDOT PDP, and NCHRP 08-60.
Sheets
• Default Categories — master list of risk categories used to group risks. CatIDs are referenced from the Default Risks sheet.
• Default Risks — master risk library. Each row is one risk event, tagged with primary impact (Cost / Schedule / Both), typical phase, and whether the risk applies to Non-Complex, Moderately Complex, and/or Most Complex projects. Use Excel's AutoFilter on row 1 to filter by category, impact, phase, or complexity tier.
• Project Complexity — tier-defining criteria. Use the most demanding column that matches the project; the column you pick should also be the complexity column you filter by in Default Risks.
How to use
1. Identify the project's complexity tier using the Project Complexity sheet.
2. Filter Default Risks on the tier column = "X" to get the candidate risk list.
3. Review with the project team; remove risks that genuinely do not apply and add project-specific risks.
4. Carry the resulting list into the project risk register, where each risk is scored for probability, cost/schedule impact, and assigned an owner and response strategy.
Conventions
• Primary Impact: Cost = risk primarily drives cost. Schedule = risk primarily drives schedule. Both = both.
• Typical Phase: Planning, PE/Design, ROW, Environmental, Procurement, Construction, or All.
• Tier columns: an "X" means the risk typically applies to that tier. Risks unmarked for a tier are still possible but less common.

## Sources
Caltrans Project Risk Management Handbook
WSDOT Project Risk Management Guide / CEVP
FDOT Major Projects CSRA (PMG 405)
GDOT Plan Development Process
FHWA Major Projects PMP Guidance
FHWA Guide to Risk Assessment and Allocation for Highway Construction
NCHRP 08-60 Risk Analysis Guidebook

## Default Categories
CatID | Category
SCP | Scope
SCH | Schedule
ESTI | Estimate
DES | Design
GEO | Geotechnical
SITE | Site Conditions
STR | Bridge & Structures
PVT | Pavement
HYD | Hydraulic / Drainage / Stormwater
ENV | Environmental
CULT | Cultural & Historic
RW | Right-of-Way
UTL | Utility
RR | Railroad
TP | Third-Party
PUB | Public Involvement / Stakeholder
CNTR | Procurement & Contract
CN | Construction
QC | Quality / QA-QC
SAF | Safety / Health
ITS | ITS / Technology
MRK | Market / Escalation
FUND | Funding
ORG | Organizational / Project Controls
EXT | External / Force Majeure

## Default Risks
CatID | Risk Category | Risk Event Name | Risk Description | Primary Impact | Typical Phase | Non-Complex | Moderately Complex | Most Complex
SCP | Scope | Incomplete scope definition | Project purpose, need, and scope are poorly or incompletely defined at programming. | Both | Planning | X | X | X
SCP | Scope | Scope creep | Stakeholders add features or refinements after the baseline scope is set. | Both | PE/Design | X | X | X
SCP | Scope | Late betterments | Local agency or stakeholder requests additional scope (e.g., aesthetics, added improvements) after PS&E. | Both | PE/Design | X | X | X
SCP | Scope | Design standard or criteria change | Mid-project change to design standards (AASHTO, agency manual) increases scope. | Both | PE/Design |  | X | X
SCP | Scope | Phasing or segmentation change | Project is broken into phases or recombined after baseline, changing logic and cost. | Both | Planning |  | X | X
SCP | Scope | Project purpose & need change | Purpose and need are revised after environmental documentation begins. | Both | Planning |  | X | X
SCH | Schedule | Aggressive baseline schedule | Baseline duration is unrealistic for the project's design and approvals scope. | Schedule | Planning | X | X | X
SCH | Schedule | Scheduling errors | Errors in schedule logic, durations, or resource loading. | Schedule | All | X | X | X
SCH | Schedule | Inaccurate contract time estimate | Contract time (working days / completion date) under-estimated relative to scope. | Schedule | PE/Design | X | X | X
SCH | Schedule | Concurrent task slip | Parallel activities (e.g., ROW, environmental, utilities) fail to align with PS&E. | Schedule | All | X | X | X
SCH | Schedule | Letting slip | PS&E not ready for advertised letting date. | Schedule | Procurement | X | X | X
SCH | Schedule | Restricted work windows | Environmental, in-water, fish, or night-only work windows compress the schedule. | Schedule | Construction | X | X | X
SCH | Schedule | Resource constraint | Agency staff or consultant resources insufficient to deliver on schedule. | Schedule | All | X | X | X
ESTI | Estimate | Estimate errors and omissions | Errors or omitted pay items in the cost estimate. | Cost | PE/Design | X | X | X
ESTI | Estimate | Quantity growth | Final quantities exceed estimating-stage take-offs. | Cost | PE/Design | X | X | X
ESTI | Estimate | Unit price inaccuracy | Historical unit prices are not representative of the current bid environment. | Cost | PE/Design | X | X | X
ESTI | Estimate | Inadequate contingency | Risk-allocated contingency is below CSRA-recommended level for the project's risk profile. | Cost | Planning | X | X | X
ESTI | Estimate | Inflation to mid-point of construction | Inflation between estimate basis date and the mid-point of construction. | Cost | All | X | X | X
ESTI | Estimate | Inexperienced estimator | Estimator lacks experience or familiarity with the work type. | Cost | PE/Design | X | X | X
ESTI | Estimate | Inconsistent estimating procedure | No standard procedure / documentation leads to inconsistent estimates across phases. | Cost | PE/Design | X | X | X
ESTI | Estimate | Inaccurate unit price database | Unit price database contains errors, omissions, or is not updated. | Cost | PE/Design | X | X | X
ESTI | Estimate | Limited independent estimate review | Lack of independent (3rd party / HQ) review of the estimate before key decisions. | Cost | PE/Design |  | X | X
DES | Design | Design errors and omissions | Plan/specification defects discovered after letting or during construction. | Both | Construction | X | X | X
DES | Design | Late design changes | Owner-directed revisions after 90% PS&E milestone. | Both | PE/Design | X | X | X
DES | Design | Discipline coordination conflicts | Gaps between roadway, structures, drainage, ITS, and traffic disciplines. | Both | PE/Design | X | X | X
DES | Design | Design exceptions | Design exceptions or non-standard features require additional approvals and risk. | Both | PE/Design | X | X | X
DES | Design | Inaccurate design assumptions | Design built on assumptions (traffic, soils, hydraulics) later proven incorrect. | Both | PE/Design | X | X | X
DES | Design | Constructability issues | Design cannot be efficiently built as drawn (access, MOT, sequencing). | Both | Construction | X | X | X
DES | Design | Architectural / landscape changes | Late changes to aesthetics or landscape add cost and delay. | Both | PE/Design | X | X | X
DES | Design | Regulatory or criteria change impacts design | Mid-project regulatory change forces redesign (e.g., emissions, safety, ADA, Buy America). | Both | PE/Design |  | X | X
DES | Design | Design / PS&E review delays | Internal or external design reviews delay milestone delivery. | Schedule | PE/Design | X | X | X
DES | Design | Project acceleration pressure | Pressure to deliver on an accelerated schedule compresses design quality. | Both | PE/Design |  | X | X
DES | Design | Impacts to other agency projects | Design impacts to or from adjacent agency projects require coordination. | Both | PE/Design |  | X | X
GEO | Geotechnical | Differing site conditions | Subsurface materials differ materially from contract boring data. | Both | Construction | X | X | X
GEO | Geotechnical | Inadequate geotechnical investigation | Borings or testing program too sparse for design risk. | Both | PE/Design | X | X | X
GEO | Geotechnical | Poor / unsuitable soils | Native soils require treatment, removal, or replacement. | Both | Construction | X | X | X
GEO | Geotechnical | Unsound subgrade | Subgrade requires undercut or stabilization beyond baseline scope. | Both | Construction | X | X | X
GEO | Geotechnical | Adverse groundwater conditions | Unanticipated groundwater requires dewatering or design change. | Both | Construction | X | X | X
GEO | Geotechnical | Boulders or buried obstructions | Unexpected boulders, debris, or buried obstructions in soils. | Both | Construction | X | X | X
GEO | Geotechnical | Slope instability / landslide | Active or latent slope instability encountered during cut or fill. | Both | Construction |  | X | X
GEO | Geotechnical | Liquefaction / seismic settlement | High-seismic site requires ground improvement or specialized foundations. | Both | PE/Design |  |  | X
GEO | Geotechnical | Karst / mine subsidence | Karst features, sinkholes, or abandoned mines require investigation and treatment. | Both | PE/Design |  | X | X
SITE | Site Conditions | Late or erroneous surveys | Field surveys are delivered late, in error, or both. | Both | PE/Design | X | X | X
SITE | Site Conditions | Hazardous waste discovery | Hazardous waste site analysis incomplete or new contamination discovered. | Both | Construction | X | X | X
SITE | Site Conditions | Unanticipated existing infrastructure | Abandoned utilities, footings, or other infrastructure discovered during excavation. | Both | Construction | X | X | X
SITE | Site Conditions | Site access limitations | Limited physical access for investigation, staging, or hauling. | Both | Construction | X | X | X
STR | Bridge & Structures | Foundation type redesign | Pile, shaft, or footing depth/type changes after subsurface review. | Both | PE/Design |  | X | X
STR | Bridge & Structures | Seismic retrofit scope growth | Existing-structure retrofit scope expands beyond baseline. | Both | PE/Design |  |  | X
STR | Bridge & Structures | Erection method risk | Falsework, cranes, launching, or strand-jack issues with traffic open. | Both | Construction |  | X | X
STR | Bridge & Structures | In-water work window compression | Restricted in-water windows compress structure construction schedule. | Schedule | Construction |  | X | X
STR | Bridge & Structures | Long-lead structural steel / fabrication | Structural steel or precast fabrication and delivery slip. | Both | Procurement |  | X | X
STR | Bridge & Structures | Non-standard / complex structure | Unusual (segmental, cable-stayed, movable, arch) structure adds design and construction risk. | Both | PE/Design |  |  | X
STR | Bridge & Structures | Sharp skew or curved girder issues | Highly skewed or horizontally curved structures require advanced analysis and detailing. | Both | PE/Design |  | X | X
STR | Bridge & Structures | Bridge demolition complications | Demolition over traffic, water, or sensitive areas complicates removal. | Both | Construction |  | X | X
STR | Bridge & Structures | Existing structure condition worse than expected | Concealed deterioration discovered during demolition or rehab. | Both | Construction | X | X | X
PVT | Pavement | Pavement type selection change | Late change between asphalt and concrete pavement strategy. | Cost | PE/Design | X | X | X
PVT | Pavement | Subgrade failure during construction | Existing subgrade requires undercut, stabilization, or geosynthetics. | Both | Construction | X | X | X
PVT | Pavement | Smoothness / IRI specification miss | Pavement smoothness target missed; incentives lost or corrective work required. | Cost | Construction | X | X | X
PVT | Pavement | Mix design or binder availability | Specified mix, binder, or recycled-content material not regionally available. | Both | Construction | X | X | X
PVT | Pavement | Existing pavement condition worse than expected | Discovered distresses require deeper rehabilitation than scoped. | Both | Construction | X | X | X
HYD | Hydraulic / Drainage / Stormwater | Floodplain or USACE permit change | FEMA or USACE permit conditions change project scope. | Both | Environmental | X | X | X
HYD | Hydraulic / Drainage / Stormwater | Scour countermeasures required | Scour analysis triggers countermeasures not in baseline. | Both | PE/Design |  | X | X
HYD | Hydraulic / Drainage / Stormwater | Stormwater BMP expansion | MS4 / NPDES requirements expand treatment footprint or BMP type. | Both | PE/Design | X | X | X
HYD | Hydraulic / Drainage / Stormwater | Existing drainage system inadequate | Downstream system found undersized during construction. | Both | Construction | X | X | X
HYD | Hydraulic / Drainage / Stormwater | Hydraulic redesign of major drainage | Bridge hydraulics or culvert sizing redesign during PE. | Both | PE/Design |  | X | X
ENV | Environmental | NEPA class of action change | Project bumps from Categorical Exclusion to EA or EA to EIS. | Schedule | Environmental | X | X | X
ENV | Environmental | Environmental permit delays | 404/401, USFWS, NMFS, or air permits delayed in review or coordination. | Schedule | Environmental | X | X | X
ENV | Environmental | Environmental document review delay | Delay in agency or public review of environmental documentation. | Schedule | Environmental | X | X | X
ENV | Environmental | Environmental regulation change | Regulatory change after baseline (e.g., species listings, air standards). | Both | Environmental | X | X | X
ENV | Environmental | Wetland / habitat mitigation growth | Wetland or habitat mitigation ratios, sites, or scope grow. | Both | Environmental | X | X | X
ENV | Environmental | Threatened & endangered species impacts | T&E listing or critical habitat constrains work windows or design. | Both | Environmental | X | X | X
ENV | Environmental | Noise mitigation (soundwalls) | Permanent noise mitigation (additional soundwalls) required. | Cost | PE/Design | X | X | X
ENV | Environmental | Environmental analysis on new alignment | Environmental analysis required on new alignment or alternative. | Both | Environmental |  | X | X
ENV | Environmental | Hazardous materials discovery (construction) | Contaminated soils, asbestos, or lead paint discovered during construction. | Both | Construction | X | X | X
ENV | Environmental | Title VI / Environmental Justice | EJ analysis triggers additional mitigation or community commitments. | Both | Environmental | X | X | X
CULT | Cultural & Historic | Section 106 adverse effect | Historic property adverse-effect finding requires MOA and mitigation. | Both | Environmental | X | X | X
CULT | Cultural & Historic | Archaeological discovery | Unanticipated archaeological discovery triggers stop-work or Phase III. | Schedule | Construction | X | X | X
CULT | Cultural & Historic | Tribal consultation delay | Tribal consultation under Section 106 / NHPA delays clearance. | Schedule | Environmental |  | X | X
RW | Right-of-Way | ROW acquisition delay | Negotiation, appraisal, or possession milestones slip. | Schedule | ROW | X | X | X
RW | Right-of-Way | Condemnation / eminent domain | Order of possession is contested in court or delayed. | Both | ROW | X | X | X
RW | Right-of-Way | Relocation of occupants / businesses | Replacement housing or business relocation cost overruns. | Cost | ROW | X | X | X
RW | Right-of-Way | Access control change | Access management decisions (e.g., IJR/IMR outcomes) modify takings. | Both | ROW |  | X | X
RW | Right-of-Way | Late parcel additions | Design refinement adds parcels after the ROW baseline. | Both | ROW | X | X | X
RW | Right-of-Way | ROW inflation | Property values rise faster than estimating-stage inflation. | Cost | ROW | X | X | X
RW | Right-of-Way | Limited access constraints | Limited access provisions (IJR) or cemetery / sensitive parcels constrain ROW. | Both | ROW |  | X | X
UTL | Utility | Utility conflict not identified | SUE / mapping missed conflicts surface during construction. | Both | Construction | X | X | X
UTL | Utility | Utility relocation delay | Utility owner's relocation schedule slips against PS&E or construction. | Schedule | PE/Design | X | X | X
UTL | Utility | Utility agreement / reimbursement dispute | Cost-share, prior-rights, or betterment dispute with utility owner. | Cost | PE/Design | X | X | X
UTL | Utility | Major transmission / substation relocation | High-voltage transmission, substation, or fiber backbone relocation required. | Both | Construction |  | X | X
UTL | Utility | Buried hazards / abandoned utilities | Unknown abandoned utilities encountered during excavation. | Both | Construction | X | X | X
RR | Railroad | C&M agreement delay | Construction & Maintenance agreement with railroad delays project. | Schedule | PE/Design |  | X | X
RR | Railroad | Railroad flagging cost / availability | Railroad flaggers limited; flagging cost or schedule escalation. | Cost | Construction |  | X | X
RR | Railroad | Railroad force-account work | Railroad force-account scope or cost exceeds budget. | Cost | Construction |  | X | X
RR | Railroad | Track outage window limits | Limited track outage windows compress construction. | Schedule | Construction |  | X | X
RR | Railroad | Railroad coordination breakdown | Poor communication with railroad leads to delays. | Schedule | All |  | X | X
RR | Railroad | Construction requirements near rail | Additional requirements (clearances, protective measures) due to proximity to rail. | Both | Construction |  | X | X
TP | Third-Party | Local / county agency review delay | City / county plan review, permit, or approval lags. | Schedule | PE/Design | X | X | X
TP | Third-Party | Government agency coordination | Coordination with other government agencies (FHWA, USACE, USFWS, NMFS). | Schedule | Environmental | X | X | X
TP | Third-Party | Adjacent project conflict | Concurrent adjacent project blocks staging, detours, or MOT. | Both | Construction | X | X | X
TP | Third-Party | Intergovernmental agreement delay | Intergovernmental agreements or jurisdictional handoffs delay the project. | Schedule | PE/Design | X | X | X
TP | Third-Party | Third-party cost increase | Third-party requests increase cost during construction (e.g., betterments). | Cost | Construction | X | X | X
TP | Third-Party | Federal land manager coordination | USFS, BLM, NPS, or other federal land manager coordination required. | Schedule | Environmental |  | X | X
PUB | Public Involvement / Stakeholder | Organized public opposition | Organized opposition triggers redesign, scope change, or delay. | Both | Planning | X | X | X
PUB | Public Involvement / Stakeholder | Elected-official intervention | Political pressure forces scope, schedule, or alignment change. | Both | All | X | X | X
PUB | Public Involvement / Stakeholder | Community impact concerns | Local community objections require additional mitigation or outreach. | Both | PE/Design | X | X | X
PUB | Public Involvement / Stakeholder | Media or social-media campaign | Negative coverage or social-media campaign delays approvals. | Schedule | All |  | X | X
PUB | Public Involvement / Stakeholder | Stakeholder scope additions | Influential stakeholders request additional scope for commercial / community ends. | Both | PE/Design | X | X | X
CNTR | Procurement & Contract | Bids over engineer's estimate | All bids exceed the budget and re-letting may be required. | Both | Procurement | X | X | X
CNTR | Procurement & Contract | Insufficient bidders / limited competition | Limited number of bidders raises bid prices or quality risk. | Cost | Procurement | X | X | X
CNTR | Procurement & Contract | Late change in delivery method | Late change in delivery method (DBB / DB / CMGC / P3) delays award. | Schedule | Procurement |  | X | X
CNTR | Procurement & Contract | Ambiguous contract language | Ambiguities in contract documents drive disputes and delays. | Both | Construction | X | X | X
CNTR | Procurement & Contract | Advertising / bid / award delays | Advertising, bidding, or award milestones slip. | Schedule | Procurement | X | X | X
CNTR | Procurement & Contract | Procurement staffing | Insufficient staff to process procurement actions. | Schedule | Procurement | X | X | X
CNTR | Procurement & Contract | Contractor non-performance | Awarded contractor fails to perform, leading to default or termination. | Both | Construction | X | X | X
CNTR | Procurement & Contract | Specialty contractor availability | Specialty subcontractor (e.g., bridge erection, structural steel) not available. | Both | Procurement |  | X | X
CNTR | Procurement & Contract | DBE participation shortfall | DBE goal not met; certification or compliance issues delay award. | Schedule | Procurement | X | X | X
CNTR | Procurement & Contract | Bid protest | Award protest delays Notice to Proceed. | Schedule | Procurement |  | X | X
CN | Construction | Change-order growth | Cumulative change orders exceed allocated contingency. | Cost | Construction | X | X | X
CN | Construction | Claims and disputes | Contractor claims for delay, differing site conditions, or impacts. | Both | Construction | X | X | X
CN | Construction | Construction sequencing / staging issues | Problems with sequencing, staging, or phasing as designed. | Both | Construction | X | X | X
CN | Construction | Maintenance of traffic / work-zone control | MOT / work-zone traffic control issues drive cost or delay. | Both | Construction | X | X | X
CN | Construction | Contractor access / staging constraints | Insufficient ROW or laydown for contractor access and staging. | Both | Construction | X | X | X
CN | Construction | Earthwork access and reuse | Earthwork issues associated with material reuse and haul access. | Both | Construction | X | X | X
CN | Construction | Marine / over-water construction | Limited access, barge logistics, or tidal constraints for marine work. | Both | Construction |  | X | X
CN | Construction | Construction permitting delays | Construction-stage permits (encroachment, dewatering) delayed. | Schedule | Construction | X | X | X
CN | Construction | Project acceleration during construction | Pressure to accelerate construction drives overtime, change, and risk. | Both | Construction | X | X | X
CN | Construction | Acceptance / punch-list closeout | Acceptance process drags out final completion and warranty start. | Schedule | Construction | X | X | X
CN | Construction | Detour viability / public acceptance | Planned detour not acceptable to local agency or the public. | Both | Construction | X | X | X
CN | Construction | Night-work / lane-rental productivity | Restrictive work hours impair productivity. | Both | Construction | X | X | X
QC | Quality / QA-QC | Materials non-conformance | Mix, concrete, or steel fails acceptance testing. | Both | Construction | X | X | X
QC | Quality / QA-QC | QC/QA process issues | QC/QA program inadequate, leading to rework or disputes. | Both | Construction | X | X | X
QC | Quality / QA-QC | Independent assurance findings | IA findings force retesting and rework. | Both | Construction | X | X | X
QC | Quality / QA-QC | Warranty exposure | Warranty defects discovered during close-out or warranty period. | Cost | Construction | X | X | X
SAF | Safety / Health | Work-zone crash | Serious work-zone incident triggers shutdown, redesign, or penalties. | Both | Construction | X | X | X
SAF | Safety / Health | Worker injury / OSHA event | Serious worker injury or fatality triggers stoppage and investigation. | Both | Construction | X | X | X
SAF | Safety / Health | Public exposure incident | Falling object, hazardous material exposure, or property damage to public. | Both | Construction | X | X | X
SAF | Safety / Health | High accident potential work | Work activities with elevated accident potential (e.g., heights, confined space). | Both | Construction | X | X | X
ITS | ITS / Technology | ITS scope late-defined | ITS devices, communications, and integration scope incomplete at PS&E. | Both | PE/Design |  | X | X
ITS | ITS / Technology | TMC integration failure | Integration with Traffic Management Center fails or slips. | Both | Construction |  | X | X
ITS | ITS / Technology | Tolling / managed-lanes system | Toll system integrator delay or non-performance. | Both | Construction |  |  | X
ITS | ITS / Technology | Communications backbone availability | Fiber or wireless backhaul not available when needed. | Schedule | Construction |  | X | X
MRK | Market / Escalation | Asphalt / liquid binder price spike | Liquid asphalt or AC index spikes above contract escalator. | Cost | Construction | X | X | X
MRK | Market / Escalation | Steel price or availability | Structural steel or rebar price volatility or availability. | Cost | Procurement | X | X | X
MRK | Market / Escalation | Fuel cost escalation | Diesel and fuel cost spikes affect contractor pricing. | Cost | Construction | X | X | X
MRK | Market / Escalation | Cement / concrete shortage | Regional cement or aggregate shortage drives substitutions. | Both | Construction | X | X | X
MRK | Market / Escalation | Labor shortage / wage growth | Craft labor scarcity drives up bid prices and slows progress. | Cost | Procurement | X | X | X
MRK | Market / Escalation | Contractor availability | Limited number of qualified contractors in the regional market. | Cost | Procurement | X | X | X
MRK | Market / Escalation | Buy America / domestic content | Buy America compliance impacts availability of steel, iron, or construction materials. | Both | Procurement | X | X | X
FUND | Funding | Funding availability shortfall | Project funding not fully available when needed. | Schedule | All | X | X | X
FUND | Funding | Federal-aid authorization delay | Apportionment, obligation, or reauthorization timing impacts letting. | Schedule | Procurement | X | X | X
FUND | Funding | Discretionary grant not awarded | Discretionary federal grant (e.g., BUILD, INFRA, Mega, Bridge Investment) not received. | Both | Planning |  | X | X
FUND | Funding | State funding shortfall | Gas-tax, motor-vehicle, or general-fund shortfall reduces available funds. | Both | All | X | X | X
FUND | Funding | Cash-flow / annual ceiling constraint | Annual funding ceiling forces schedule extension. | Schedule | Construction |  | X | X
FUND | Funding | Funding priority change | Reprioritization of funding moves the project lower in the program. | Schedule | All | X | X | X
ORG | Organizational / Project Controls | PM or key staff turnover | Loss of PM, lead designer, or other critical staff at a crucial point. | Both | All | X | X | X
ORG | Organizational / Project Controls | Inexperienced staff | Inexperienced agency or consultant staff assigned to key roles. | Both | All | X | X | X
ORG | Organizational / Project Controls | Insufficient staffing capacity | Functional units overloaded by too many concurrent projects. | Schedule | All | X | X | X
ORG | Organizational / Project Controls | Internal decision latency | Internal approvals or decisions slow at critical milestones. | Schedule | All | X | X | X
ORG | Organizational / Project Controls | Communication breakdown | Lack of coordination or communication within the project team. | Both | All | X | X | X
ORG | Organizational / Project Controls | Local Public Agency (LPA) capability | Local Public Agency lacks the capacity or experience to execute Federal-aid work. | Both | All | X | X | X
ORG | Organizational / Project Controls | Project-controls maturity | Schedule and cost baselines not credibly maintained or updated. | Both | All |  | X | X
ORG | Organizational / Project Controls | Consultant performance | A&E consultant deliverables late or of inadequate quality. | Both | PE/Design | X | X | X
EXT | External / Force Majeure | Severe weather | Hurricane, flood, wildfire, severe winter, or extreme heat disrupts work. | Schedule | Construction | X | X | X
EXT | External / Force Majeure | Seismic event | Earthquake during design or construction in high-seismic regions. | Both | Construction |  |  | X
EXT | External / Force Majeure | Pandemic / public health event | Public health emergency forces stand-down or restrictions. | Schedule | All | X | X | X
EXT | External / Force Majeure | Litigation | NEPA, ROW, DBE, or other lawsuit halts or delays the project. | Schedule | All | X | X | X
EXT | External / Force Majeure | Regulatory / policy change | New federal or state regulation or policy change impacts the project. | Both | All | X | X | X
EXT | External / Force Majeure | Political / administration change | Change in administration shifts project priorities or funding. | Both | All |  | X | X

## Project Complexity
Project Complexity Tiers — Highway Construction Projects
Source guidance: FHWA Major Projects program (≥ $500M PMP/CSRA), FDOT PMG 405, WSDOT Project Risk Management Guide / CEVP, Caltrans PRMHB (Levels 1/2/3), GDOT PDP, NCHRP 08-60. Use the most demanding column that matches the project.
Criterion | Non-Complex | Moderately Complex | Most Complex
Roadway | Resurfacing, restoration, minor safety, signing/striping, guardrail, ADA, minor culvert; single-discipline. | 3R/4R reconstruction, capacity adding/widening on existing alignment, new conventional interchange, multi-phase MOT. | New highways on new alignment, major reconstruction with CPM-required MOT, complex interchange reconfiguration.
Structures | No bridge work, minor deck overlay, conventional culvert replacement, single-span standard bridge. | Conventional bridge replacement, moderate span, standard skew/curvature, bridge cost typically below $25M. | Unusual structures (segmental, cable-stayed, movable, major arch/truss), sharp skew (<70°), curved girders, complex seismic, bridge cost ≥ $25M or meeting FHWA Major Bridge definition.
Foundations | Conventional spread footings or short driven piles; routine subsurface. | Driven piles, drilled shafts, modest ground improvement. | Caissons, deep drilled shafts, ground improvement at scale, karst / mine / liquefaction mitigation.
Traffic Control / MOT | Single-stage closure, off-peak detour, or simple shoulder work. | Multi-phased MOT with detours; CPM scheduling for traffic-staging required. | Multi-phase traffic control with major detours, lane-rental, full closures, and CPM mandatory; major ITS or ATMS corridor.
Right-of-Way | No or minimal ROW; minor temporary easements. | Moderate ROW (a few to ~20 parcels), some residential or commercial relocations, limited condemnation. | Numerous parcels, complex commercial/industrial displacement, condemnation likely, environmental clean-up of acquired parcels, access control changes.
Utilities | Minimal utility coordination, distribution-level conflicts only. | Multi-utility coordination, distribution and limited transmission, conventional relocations. | Major utility relocations (transmission lines, substations, fiber backbone), heavy multi-utility coordination.
Railroad | No railroad involvement. | Crossing improvements or minor work near rail; standard C&M agreement. | Work over or adjacent to active mainline, complex C&M and force-account, restricted track outage windows.
Environmental | Categorical Exclusion (CE); minimal resource impacts. | Environmental Assessment (EA); some wetland/habitat/cultural impacts; standard 404/401 permits. | Environmental Impact Statement (EIS) or complex EA; multiple resource agencies (FHWA, USACE, USFWS, NMFS, EPA, Tribal); T&E species, Section 4(f), 106 adverse effect; multiple-alternatives analysis.
Stakeholders / Public | No public controversy, routine outreach. | Moderate stakeholder coordination, elected-official briefings, routine public meetings. | Controversial, high-profile, fast-track project; intense elected-official involvement; numerous stakeholders; sustained media attention.
Funding / Delivery | Single-source state or federal-aid funding; design-bid-build. | Multiple funding sources, possible discretionary grant; design-bid-build or design-build. | Multiple funding sources including discretionary federal grant; design-build, CMGC, P3, or other alternative delivery; FHWA Major Project (≥ $500M) requiring PMP and CSRA.
Schedule | Routine duration; flexible let date. | Defined letting and completion milestones; some external dependencies. | Hard-constrained letting and completion (grant agreement, event-driven); heavily interdependent milestones.
Risk Register Level | Qualitative risk identification; brief register; periodic review. | Qualitative + semi-quantitative risk analysis; risk register maintained through PE; periodic CSRA-light. | Full Cost & Schedule Risk Analysis (CSRA) per FHWA Major Projects guidance; quantitative Monte Carlo; risk register actively managed through close-out.